Post-Restructure Retention and Performance Framework

Your restructure has been announced. Some roles have been made redundant, others have changed, and the organisation is now in the most fragile phase of the change cycle. The departures are visible; the attrition risk among remaining staff is invisible. Research consistently shows that voluntary turnover peaks in the 6–12 weeks following a restructure announcement — not because the restructure itself was wrong, but because it triggers a reassessment among high performers who were already considering their options. This framework gives you the structured process to monitor retention risk, reset performance expectations for changed roles, identify and address early disengagement, and stabilise the organisation in the 90 days that determine whether the restructure was a success.

| Tool | Post-Restructure Retention and Performance Framework |
| --- | --- |
| Bundle | Workforce Change Management Bundle |
| Vertical | HR and Talent Management |
| Format | Framework |

FOR LEADERSHIP The primary risk in the post-restructure period is not the employees who left — it is the employees who stayed but have mentally checked out. Survivor syndrome is well-documented: remaining staff frequently experience guilt, anxiety, increased workload, and reduced confidence in leadership. If it is not actively managed, it manifests as disengagement, reduced performance, and voluntary attrition among the people you most need to keep. For gambling operators, the compliance risk dimension makes this particularly acute: if your best compliance, RG, or AML staff leave in the post-restructure period, you are simultaneously managing a regulatory gap and a talent crisis. This framework addresses retention, performance, and engagement in the 90-day window that matters most.

FOR THE MANAGER USING THIS TOOL This framework works in four parts. Part 1 is the 30-day stabilisation phase — the immediate actions required in the first month. Part 2 is the retention risk management framework — how to identify and act on individual flight risk before it becomes resignation. Part 3 is the performance reset — how to establish clear expectations and support for employees in changed or new roles. Part 4 is the 90-day review process — the structured assessment of whether the post-restructure organisation is performing and what still needs to be addressed. Run this framework in parallel with normal operations — it is not a one-off project but a structured management discipline for 90 days.

OPERATOR TIP The most important conversation you can have in the first two weeks is not with your high performers — they will manage. It is with your mid-tier performers who are now carrying significantly more work than before. They will not tell you they are struggling. They will quietly update their LinkedIn profile. Build a specific check-in cadence for this group. The question to ask is not "how are you finding things?" — it is "what is the one thing that would make the biggest difference to your workload right now?"

# Part 1 — 30-Day Stabilisation

The first 30 days determine the tone. These actions should be completed within the first month.

## 1.1  Immediate Actions (Week 1–2)

| Action | Owner | Due | Done |
| --- | --- | --- | --- |
| All-team briefing: new structure explained, workload transition plan confirmed, no further changes coming (if true) | Senior leader | Week 1 |  |
| Individual 1:1 with every direct report: check in, not performance management. Listen first. | Each line manager | Week 1–2 |  |
| Workload audit: identify where departures have created coverage gaps or unrealistic loads | HR + line managers | Week 2 |  |
| EAP (Employee Assistance Programme) re-communicated to all staff | HR | Week 1 |  |
| Compliance function check: confirm all regulatory obligations are covered with named owners | Compliance Director | Week 1 |  |
| Voluntary attrition report: any resignation in week 1 is a signal — review with HR immediately | HR Director | Week 1 |  |

## 1.2  Stabilisation Checks (Week 3–4)

| Check | Finding | Action |
| --- | --- | --- |
| Team capacity: is the remaining team able to absorb the workload without unsustainable pressure? |  |  |
| Role clarity: does everyone understand their new or changed responsibilities? |  |  |
| Decision authority: are new reporting lines and decision rights clear? |  |  |
| Informal team dynamics: any dysfunction, blame, or rumour cycles emerging? |  |  |

# Part 2 — Retention Risk Management

Identify and actively manage flight risk for the individuals the business most needs to retain.

## 2.1  Retention Risk Assessment

Rate each key individual using the framework below. Update monthly.

| Risk Factor | Low Risk | Medium Risk | High Risk |
| --- | --- | --- | --- |
| Engagement signals | Active, visible, contributing | Quieter than usual, reduced volunteering | Withdrawn, disengaged, reduced effort |
| External market activity | No visible signals | LinkedIn updated recently | Active job search signals or recruiter contact disclosed |
| Relationship with new manager or structure | Positive, adapting well | Neutral, adjusting | Struggling, resistance visible |
| Workload impact | Manageable | Stretched but coping | Overloaded — expressing or signalling burnout |
| Change alignment | Understands and supports the rationale | Uncertain but not resistant | Does not see a place for themselves in the new structure |

## 2.2  Retention Risk Register

| Role (by role, not name in shared version) | Risk Level | Key Driver | Retention Action | Owner | Review Date |
| --- | --- | --- | --- | --- | --- |
|  | H / M / L |  |  |  |  |

## 2.3  Retention Toolkit

| Situation | Retention Response Options |
| --- | --- |
| High performer, workload is the issue | Temporary resource support / contractor cover; explicit recognition; timeline to normalisation |
| High performer, role clarity is the issue | Clear scope conversation; documented role brief; decision authority confirmed |
| High performer, career pathway unclear | Career conversation — what does progression look like in the new structure? |
| Mid-tier performer, disengaged | Manager-led re-engagement: what would make this role work better for you? |
| Critical compliance/RG/AML role at risk | Escalate to HR Director; consider retention payment; assess regulatory risk if role departs |

# Part 3 — Performance Reset

Changed and new roles require a deliberate reset of performance expectations. Do not assume existing job descriptions or previous targets carry over into a restructured role without explicit agreement.

## 3.1  Role Clarity Conversations

Every employee in a changed role must have a documented conversation confirming:

| Element to Confirm | Agreed? | Owner | Date |
| --- | --- | --- | --- |
| New scope and primary accountabilities | Yes / No / Pending |  |  |
| Reporting line(s) confirmed and understood | Yes / No / Pending |  |  |
| Decision authority — what can they decide without sign-off? | Yes / No / Pending |  |  |
| Performance objectives for the next 90 days | Yes / No / Pending |  |  |
| Development support available (training, coaching, peer shadowing) | Yes / No / Pending |  |  |
| For regulated roles: LCCP/compliance accountabilities confirmed unchanged or updated | Yes / No / N/A |  |  |

## 3.2  90-Day Performance Objectives

Set specific, achievable objectives for the first 90 days in any changed role. These should reflect stabilisation and relationship-building, not transformational delivery.

| Objective | Success Criteria | Due Date | Status |
| --- | --- | --- | --- |

# Part 4 — 90-Day Review

## 4.1  Organisational Health Indicators

| Metric | Week 4 | Week 8 | Week 12 | Target |
| --- | --- | --- | --- | --- |
| Voluntary turnover (resignations, annualised) |  |  |  | Below pre-restructure baseline |
| Absence rate |  |  |  | Below industry average |
| Open vacancies (new departures creating gaps) |  |  |  | 0 unexpected vacancies in critical roles |
| Employee sentiment — pulse survey or 1:1 signals |  |  |  | Improving from week 4 baseline |
| Compliance function staffing — all roles filled or covered |  |  |  | 100% covered |

## 4.2  90-Day Assessment

Overall assessment of post-restructure stability:

Red / Amber / Green

Key achievements in the first 90 days:

Remaining issues to address:

Any regulatory obligations or PML/KI gaps still open:

Actions required for the next 90 days:

| Priority Action | Owner | Due Date | Status |
| --- | --- | --- | --- |